## Sprint0
Sl	Tasks	Sub Tasks	Status	Estimate
1	Prep Project		Complete
		Environment	Complete
		Back End	Complete
		Front End	Complete
2	Setup Environment		Complete
3	Softwares Required		Complete
4		Git Setup	Complete
5		ER Diagram	Complete
6		Flow Chart Tool	Complete
7		Wire Frame Tool	Complete

## Sprint1
Sl	Tasks	Sub Tasks	Status	Estimate	Time Consumed
1	User Login
		Design mockup Sign In/Register	Complete
		Setup React App
		Write Test Cases
		Implement Landing Pages
		Implement Routes
		Test Setup
		Automate Unit Tests

		Design Api signatures for login/logout/register/reset	Complete
		Setup Node App
		Write Test Cases
		implement user routes
		Connect to mail server
		Implement reset password
		Test Setup
		Automate Unit Tests

2	User Profile
		Design Mockup for user profile
		Implement User Profiles
		Unit Tests

		Design Api Signature for user profile
		Implement routes
		Unit Tests

## BackLog
Sl	Task
1	Design Logo

## Sheet3
Look Up

Status	Yet To Start
	In-Progress
	Complete
	Parked